## Sayfa1
Risk ID | Risk Description | Category | Likelihood | Impact | Mitigation Plan | Owner | Status
1 | Dependency on GEMINI API for treatment data may fail or become unavailable. | External Dependency | High | High | Implement fallback mechanisms with cached treatments. | DevOps | Open
2 | Delays in image processing due to high network latency or server issues. | Performance | Medium | High | Optimize server performance and implement retry logic. | DevOps | Open
3 | Inadequate training data may result in poor disease detection accuracy. | AI/Model Accuracy | High | High | Enhance dataset diversity and conduct regular retraining. | AI Dev | Open
4 | Security breaches affecting user data or application integrity. | Security | Medium | High | Implement advanced encryption and secure access protocols. | Security Lead | Open
5 | Server downtime impacting application availability. | Availability | Medium | High | Use redundant servers and schedule planned maintenance during off-peak hours. | DevOps | Open
6 | Unclear user interface leading to poor user adoption. | Usability | Low | Medium | Conduct user testing and iterative UI improvements. | PM | Open
7 | Third-party library updates causing integration issues. | Integration | Medium | High | Monitor updates and test changes before deployment. | DevOps | Open
8 | Hardware incompatibility with minimum application requirements. | Hardware | Low | Medium | Set clear minimum hardware requirements and provide guidance. | PM | Open
9 | Errors in data visualization on the map feature. | Visualization | Medium | Medium | Improve map testing coverage with user feedback. | QA | Open
10 | System failure during peak concurrent user activity. | Scalability | High | High | Optimize backend architecture for scalability. | DevOps | Open
11 | Misalignment of goals among team members or stakeholders | Project Management | Medium | High | Conduct alignment meetings and document decisions clearly | PM | Open
12 | Overestimation or underestimation of task durations | Timeline | High | Medium | Add buffer time in schedules and review progress regularly | PM | Open
13 | Non-compliance with legal or data security requirements | Compliance | Medium | High | Conduct compliance audits and integrate privacy-by-design | Security Lead | Open
14 | Degradation of performance during scalability testing | Scalability | Medium | High | Conduct load testing with increasing user volumes | QA | Open
15 | Delay in external data sources (e.g., GEMINI API) | External Dependency | High | High | Introduce mock services for dependency-independent development | DevOps | Open