## Sayfa1
Task | AI Tools/LLMs tried | Best AI tool/LLMs | Best Prompt/s | Problems Faced | How long it took to complete the task? | What would you improve in that AI/LLM to increase usability?
SRS Review and Correction | ChatGPT/Claude/Gemini | ChatGPT | As a project manager analyzing this SRS document in detail, conduct a section-by-section review starting with Section A, followed by A1. Purpose, and so on. Identify any missing requirements, conflicting statements, ambiguous terms, missing use cases, incorrect UML diagrams, logical inconsistencies, or technical inaccuracies. For each section, present your findings by showing the exact sentence from the SRS document and clearly explaining the identified problem along with the reasoning behind it. Do not change the original text in the SRS. Wait for my approval before proceeding to the next section. | Difficulty in generating complete diagrams with all required relationships. | 10 Hour | Enhance the ability to detect and suggest corrections for nuanced errors.
UML Creation | ChatGPT/Claude/Gemini | Claude | As a project manager, write PlantUML code for the activity diagram of the Functional Requirement below. | Gemini was inadequate; it could not fully understand what was being said, and GPT could not establish context in the activity and sequence diagrams. | 1 Hour | Improve understanding of complex system relationships for more accurate diagrams.
WBS creation | ChatGPT/Claude/Gemini | ChatGPT | Analyze the given SRS document as a project manager and break it down into task modules. Then, list only the titles of the corresponding tasks under the title of their modules. Assign each task to the respective person assuming the tasks would be done by the following roles: PM: Ayşe, TTL: İrem, Mobile Dev: Efe, AI Dev: Irmak, DevOps: Emre, QA: Pamir. Complete the analysis module by module, starting with Preliminary Work, and seek approval before proceeding to the next module. Ensure that the output includes only task titles with the assigned person written next to the task within the module title. Use the module structure: Preliminary Work, Machine Learning & AI Module, Web (Backend/Frontend), Non-Dev Tasks, and DevOps. | Struggles to break down tasks into accurate sub-tasks. | 2 Hour | Add capabilities to identify missing sub-tasks and suggest a more detailed breakdown.
Setting Task Dependencies | ChatGPT/Claude/Gemini | ChatGPT | As a project manager, create an Excel chart named "Dependencies of Plant Diseases" for work packages, including the related tasks with task codes and their dependencies. Use the following roles to determine task dependencies logically: PM: Ayşe, TTL: İrem, Mobile Dev: Efe, AI Dev: Irmak, DevOps: Emre, QA: Pamir. Ensure that tasks can have more than one dependency if required, and consider that a task cannot start until all its related predecessor tasks are completed. Additionally, ensure that the development phase begins only after PW3 (Preliminary Work: Technical Documentation) is completed. Maintain the following format: | Limited understanding of complex task hierarchies. | 2 Hour | Better handling of multi-level dependencies and clearer visualization.
Setting Task Estimations | ChatGPT/Claude/Gemini | ChatGPT | Create a chart for three-point estimations (optimistic, realistic, pessimistic) for the tasks in the "Dependencies of Plant Diseases" chart. For example, the three-point estimations for Preliminary Work should look like this: After listing all tasks and their three-point estimations, calculate and add the total work for each estimation (Optimistic Total, Realistic Total, Pessimistic Total) in a line above the "Non-Dev Tasks" section. Ensure to list only the task titles under "Non-Dev Tasks" without leaving blank spaces for their estimations. Write the chart in the specified format. | Inconsistent time estimates for tasks with varying complexities. | 2 Hour | Include context-based estimation adjustments for varying project complexities.
Gantt Chart(Scheduling) | ChatGPT/Claude/Gemini | ChatGPT | Based on the provided chart and dependencies in the uploaded file, create a Gantt chart for the project using Python(Use Python libraries like matplotlib or plotly). Ensure task assignments adhere to the specified team members (PM: Ayşe, TTL: İrem, Mobile Dev: Efe, AI Dev: Irmak, DevOps: Emre, QA: Pamir) while maintaining resource leveling. One person can work on only one task at a time. Consider task dependencies and duration to schedule tasks logically. Present the Gantt chart in a clear and structured format that aligns with the project timeline and resource allocation. write just the related python code. | Limited accuracy or adaptability for complex | 2 Hour | Improve contextual understanding and adaptability.
Risk Identification | ChatGPT/Claude/Gemini | ChatGPT | Using the provided SRS document, dependency chart, and estimation chart for the project, create a highly detailed risk register in Excel format. T he risk register should include the following columns: Risk ID, Risk Description, Category, Likelihood (Low/Medium/High), Impact (Low/Medium/High), Mitigation Plan, Owner, and Status (Open/Closed). Ensure that all potential risks are identified, categorized, and detailed thoroughly, considering the project's dependencies, time estimations, and scope outlined in the SRS. Carefully analyze all the provided documentation and ensure no critical risks are overlooked. Write the detailed risk register in a structured Excel format with precise and comprehensive information. | Limited accuracy or adaptability for complex | 2 Hour | Improve contextual understanding and adaptability.