## Sayfa1
Task |  | Optimistic Hour | Realistic Hour | Pessimistic Hour
Preliminary Work
PW1. Team Introduction |  | 1 | 2 | 3
PW2. Architectural Design |  | 5 | 8 | 12
PW3. Technical Documentation |  | 8 | 12 | 16
Machine Learning & AI Module - Data Processing
DP1. Preprocess datasets |  | 10 | 12 | 15
DP2. Implement image processing pipeline |  | 15 | 20 | 25
Machine Learning & AI Module - Model Training
MT1. Train deep learning models |  | 20 | 30 | 40
MT2. Develop disease detection algorithms |  | 25 | 35 | 50
Machine Learning & AI Module - Model Evaluation
ME1. Evaluate model performance |  | 8 | 10 | 12
ME2. Benchmark AI models |  | 10 | 12 | 15
Machine Learning & AI Module - API Integration and Resilience
API1. Integrate GEMINI API |  | 12 | 15 | 18
API2. Test fallback mechanisms |  | 8 | 10 | 12
Web - Backend
BE1. Set up backend architecture |  | 5 | 8 | 12
BE2. Implement user authentication |  | 8 | 12 | 15
BE3. Develop APIs for image upload |  | 10 | 15 | 20
BE4. Configure database |  | 12 | 18 | 25
BE5. Enable real-time data updates |  | 15 | 20 | 25
BE6. Secure APIs with tokens |  | 10 | 15 | 20
Web - Frontend
FE1. Create login and sign-up UI |  | 5 | 8 | 10
FE2. Develop Home Page |  | 10 | 12 | 15
FE3. Build disease analysis components |  | 12 | 15 | 20
FE4. Design interactive map |  | 15 | 18 | 25
FE5. Implement community page UI |  | 10 | 12 | 15
FE6. Test accessibility |  | 8 | 10 | 12
TotalDevelopment |  | 242 | 329 | 432
Non-Dev Tasks
ND1. PM | 0.05 | 12.1 | 16.45 | 21.6
ND2. TL | 0.07 | 16.94 | 23.03 | 30.24
QA1. Test Planning | 0.10 | 24.2 | 32.9 | 43.2
QA2. Functional Testing | 0.15 | 36.3 | 49.35 | 64.8
QA3. Regression Testing | 0.10 | 24.2 | 32.9 | 43.2
QA4. Performance Testing | 0.12 | 29.04 | 39.48 | 51.84
QA5. Security Testing | 0.08 | 19.36 | 26.32 | 34.56
QA6. Conduct Smoke Tests | 0.05 | 12.1 | 16.45 | 21.6
BF1. Identify and resolve bugs | 0.08 | 19.36 | 26.32 | 34.56
BF2. Verify bug fixes | 0.10 | 24.2 | 32.9 | 43.2
DO1. Staging Deployment | 0.07 | 16.94 | 23.03 | 30.24
DO2. Production Deployment | 0.03 | 7.26 | 9.87 | 12.96
Grand Total |  | 484.0 | 658.0 | 864.0